Table of NANC projects / activities to be addressed in the next six to twelve months

Developed at NANC Meeting November 16-17, 1999

| Projects/Activities ongoing and anticipated | Group assigned | Recommended Group | Timeframe |
| --- | --- | --- | --- |
| 1. Continue to finalize terms and conditions of national pooling administrator and administrator price negotiations | IMG | IMG | Once FCC order is issued |
| 2. NPA Relief issues and activities | NOWG | NOWG | ongoing |
| 3. Start on developing next overall contract requirements and NANPA selection process | NOWG | NOWG | By 2nd Q 2000 |
| 4. NANP Expansion Policy issue decisions (adopting ten digit dialing, D digit release policy, etc.) | INC | NANC | By 1st Q 2000 |
| 5. Legal Experts Working Group - issues and support (mostly for contract extensions) | Not active | Legal Experts WG | By 1st Q 2000 |
| 6. NANPA yearly evaluation / performance review | NOWG | NOWG | By 2nd Q 2000 |
| 7. Reissue of Wireless / Wireline integration report (3rd issue) | LNPA WG | LNPA WG | By 2nd Q 2000 |
| 8. Monitor concerns, aggregate, and present to NANC industry issues related to NANPAs discharging of it's responsibilities | NOWG | NOWG | ongoing |
| 9. National pooling implementation coordination | NANC | LNPA WG | Once FCC order is issued |
| 10. Cost allocation analysis for new HYBRID survey | CRWG | CRWG | By 2nd Q 2000 |
| 11. Development of pooling guidelines | INC | INC | Jan. 2000 |
| 12. Develop terms and conditions and negotiate contract for auditing | NOWG | NOWG | By 3rd Q 2000 |
| 13. Develop requirements terms and conditions and RFP for HYBRID survey selection and implementation |  | NRO | By 2nd Q 2000 |
| 14. Development of guidelines for HYBRID survey (including reseller issue) |  | INC | By 2nd Q 2000 |
| 15.Development of hybrid algorithm |  | NRO | By 1st Q 2000 |
| 16. Development of mechanized hybrid interface |  | LNPA WG | By 2nd Q 2000 |
| 17. Development of Audit guidelines | INC | INC | By 2nd Q 2000 |
| 18. Refinements of NANP Exhaust Model | NANC |  | ongoing |
| 19. Monitoring of State Pooling Trials | NRO | NRO | ongoing |
| 20. UNP definition and guidelines |  | INC | Status report March NANC |

Wednesday, November 17, 1999