## Tracking Document
This document is being presented to the NANC 9/30/15. Respectfully submitted by the IP IMG Tri-Chairs Ann Berkowitz, Valerie Cardwell and Gina Perini.
# | Item | SEPTEMBER 2014 -- Status/Updates/Remarks | OCTOBER 2014 -- Status/Updates/Remarks | NOVEMBER 2014 -- Status/Updates/Remarks | MARCH 2015 -- Status/Updates/Remarks | MAY 2015 -- Status/Updates/Remarks | SEPTEMBER 2015 -- Status/Updates/Remarks
1 | LNP and ENUM Integration | · ATIS/SIP Forum IP-NNI Task Force (IP-NNI Task Force) by Penn Pfautz (AT&T) and Jackie Voss (ATIS) 9/12/14 | · ATIS/SIP Forum IP-NNI Task Force (IP-NNI Task Force) by Penn Pfautz (AT&T) and Jackie Voss (ATIS) 10/7/14 | · ATIS/SIP Forum IP-NNI Task Force (IP-NNI Task Force) by Jackie Voss (ATIS) 11/12/14 | · ATIS/SIP Forum IP-NNI Task Force (IP-NNI Task Force) by Jackie Voss (ATIS)
|  | The IP-NNI Task Force is collaboration between ATIS and the SIP Forum, and is chartered through Q1 2015. The task force scope is limited to IP interconnection for voice services, although it is recognized that an extension of the task force is possible to address other services. • The task force is producing two documents: (1) IP Interconnection Protocol and (2) IP Interconnection Routing (Note: The charter also includes a third document dealing with IP-NNI test plans, but work has not formally started on the third document.) • Stable draft versions of both documents are expected to be available for external review on or about October 1 2014. During this external review phase, feedback to task force will be invited. • Both documents are expected to be ready for letter ballot by February 2015. ATIS PTSC and the SIP Forum will conduct separate, parallel, letter ballots. The comments from both organizations will be merged, and the IP-NNI Task Force will be responsible for resolution on all comments received. • The output documents from the IP-NNI Task Force will be jointly owned by ATIS and the SIP Forum, and will be published by each organization. • Key points summarizing the technical content of the two documents: (1)Protocol: Document is stable, with ongoing work to complete the remaining detail in preparation for external review in October. Closely follows PTSC specification for IP-NNI. (2) Routing: Documenting a small number of routing approaches that fall into two broad categories: (a) Aggregate: builds on existing PSTN databases and constructs (e.g., LERG, number blocks) to aggregate traffic into IP interconnect points. (b) Per-TN: allows numbers to be arbitrarily assigned to any IP interconnect point, independent of any PSTN constructs. (c) Documents strategies to deal with interworking scenarios where one service provider prefers the “Aggregate” approach and the other prefers the “Per-TN” approach. (d) This document will not define a single preferred approach. Instead it will provide guidelines to simplify IP interconnection, while still allowing service providers to take a “business-driven” approach and evolve their network at the speed that works for them. | Draft documents IP Interconnection Profile and IP Interconnection Routing Report will be shared with the industry by 10/10/14 with comments due 10/29/14. | Both documents have been released to various industry organizations and public comments are being sought. Technical comments should be submitted to ipnni@access.atis.org and nni@sipforum.org by December 1, 2014. Discussions are taking place over these exploders; however, participants are also encouraged to submit written contributions to the documents to support their comments/concerns.
|  | · ATIS PTSC by Penn Pfautz (AT&) and Jackie Voss (ATIS) 9/12/14 | · ATIS PTSC by Penn Pfautz (AT&) and Jackie Voss (ATIS) -- No update provided | · ATIS PTSC by Penn Pfautz (AT&) and Jackie Voss (ATIS) -- No update provided
Issue S0125 “Toll Free Service in an All IP Environment” addresses this topic.
|  | · Local Number Portability Administration – Working Group (LNPA-WG) by Bridget Alexander (JSI) 9/11/14 | · Local Number Portability Administration – Working Group (LNPA-WG) by Bridget Alexander (JSI) | · Local Number Portability Administration – Working Group (LNPA-WG) by Bridget Alexander (JSI) 11/10/14
|  | The LNPA-WG will review the ATIS NNI idea of mapping an individual TN to SBC IP addresses via a SIP URI in the NPAC SV | No report; group has not met since September. | Report from last meeting has not been approved for distribution.
The NNI anticipates a draft by October 1. Once the NNI report is received by the LNPA-WG, the WG will discuss the report and determine whether the WG can reach consensus and notify the NANC of the activity.
2 | Toll Free Services | · FoN WG Update by Mark Lancaster (AT&T) and Suzanne Addington (Sprint) 10/7/14 | · FoN WG Update by Mark Lancaster (AT&T) and Suzanne Addington (Sprint) 10/7/14 | · FoN WG Update by Mark Lancaster (AT&T) and Suzanne Addington (Sprint) 11/11/14 | · FoN WG Update by Mark Lancaster (AT&T) and Suzanne Addington (Sprint) 3/9/15
|  |  | A white paper is being advanced to the NANC regarding Geographic Routing of Toll-Free Services from FTN #4, with the recommendation to deliver to the FCC as additional information regarding that subject. | FoN did not meet in November, no update available | A white paper was presented to the NANC in January 2015 regarding Geographic Routing of Toll-Free Services. NANC members requested more time to evaluate the white paper before delivering it to the FCC.
· ATIS PTSC by by Penn Pfautz (AT&T) and Jackie Voss (ATIS) 9/12/14
Issue S0107 “Service Transition” contains a proposal for toll free service architecture evolution in the working text.
3 | Future identifiers in support of industry trends beyond the e.164 numbering plan | · FoN WG Update Suzanne Addington (Sprint) 9/8/14 | · FoN WG Update Suzanne Addington (Sprint) 11/11/14 ) | · FoN WG Update Suzanne Addington (Sprint) 11/11/14 )
· FTN 8: All IP Addressing
|  | · All IP Addressing sub-committee was created to define future identifiers in support of IP industry trends beyond the e.164 numbering plan (including M2M impacts). | No report on this item | FoN did not meet in November, no update available
4 | ENUM model | · ATIS/SIP Forum IP-NNI Task Force (IP-NNI Task Force) by Penn Pfautz (AT&T) and Jackie Voss (ATIS) 9/12/14 | · ATIS/SIP Forum IP-NNI Task Force (IP-NNI Task Force) by Penn Pfautz (AT&T) and Jackie Voss (ATIS) 10/7/14 | · ATIS/SIP Forum IP-NNI Task Force (IP-NNI Task Force) by Jackie Voss (ATIS) 11/12/14
|  | The IP-NNI Task Force is collaboration between ATIS and the SIP Forum, and is chartered through Q1 2015. The task force scope is limited to IP interconnection for voice services, although it is recognized that an extension of the task force is possible to address other services. • The task force is producing two documents: (1) IP Interconnection Protocol and (2) IP Interconnection Routing (Note: The charter also includes a third document dealing with IP-NNI test plans, but work has not formally started on the third document.) • Stable draft versions of both documents are expected to be available for external review on or about October 1 2014. During this external review phase, feedback to task force will be invited. • Both documents are expected to be ready for letter ballot by February 2015. ATIS PTSC and the SIP Forum will conduct separate, parallel, letter ballots. The comments from both organizations will be merged, and the IP-NNI Task Force will be responsible for resolution on all comments received. • The output documents from the IP-NNI Task Force will be jointly owned by ATIS and the SIP Forum, and will be published by each organization. • Key points summarizing the technical content of the two documents: (1)Protocol: Document is stable, with ongoing work to complete the remaining detail in preparation for external review in October. Closely follows PTSC specification for IP-NNI. (2) Routing: Documenting a small number of routing approaches that fall into two broad categories: (a) Aggregate: builds on existing PSTN databases and constructs (e.g., LERG, number blocks) to aggregate traffic into IP interconnect points. (b) Per-TN: allows numbers to be arbitrarily assigned to any IP interconnect point, independent of any PSTN constructs. (c) Documents strategies to deal with interworking scenarios where one service provider prefers the “Aggregate” approach and the other prefers the “Per-TN” approach. (d) This document will not define a single preferred approach. Instead it will provide guidelines to simplify IP interconnection, while still allowing service providers to take a “business-driven” approach and evolve their network at the speed that works for them. | Draft documents IP Interconnection Profile and IP Interconnection Routing Report will be shared with the industry by 10/10/14 with comments due 10/29/14. | Both documents have been released to various industry organizations and public comments are being sought. Technical comments should be submitted to ipnni@access.atis.org and nni@sipforum.org by December 1, 2014. Discussions are taking place over these exploders; however, participants are also encouraged to submit written contributions to the documents to support their comments/concerns.
· ITIF Jay Carpenter (PHONEWORD) 7/17/14
July 16, 2014 session on numbering that was presented at the Information Technology and Innovation Foundation:
§ Video of the session: http://youtu.be/ylYzcvUR-aM
§ Dr. Schulzrinne’s presentation is available at: http://www2.itif.org/2014-schulzrinne-slides.pdf
§ The event page is at: http://www.itif.org/events/foundational-elements-ip-transition-technology-behind-transition
5 | Toll Free, identify issues related to current dependence on LATA-based routing and called party based charging | · ATIS PTSC by by Penn Pfautz (AT&T) and Jackie Voss (ATIS) 9/12/14 |  | · ATIS PTSC by Penn Pfautz (AT&) and Jackie Voss (ATIS) -- No update provided
Issue S0125 “Toll Free Service in an All IP Environment” may address this in some capacity.
6 | Consider identifiers outside e.164 numbering plan
7 | Determine M2M impact (if any) for identifiers | · FoN WG Update Suzanne Addington (Sprint) 9/8/14
· FTN 8: All IP Addressing
· All IP Addressing sub-committee was created to define future identifiers in support of IP industry trends beyond the e.164 numbering plan (including M2M impacts).
8 | Create International Database Strategy Team | · ATIS/SIP Forum IP-NNI Task Force (IP-NNI Task Force) by Penn Pfautz (AT&T) and Jackie Voss (ATIS) 9/12/14
There is potential if the scope of this group is expanded, this work will be addressed by this team.
9 | Set schedule for nationwide 10 digit dialing
IP IMG NOTE: This requires action from the regulatory bodies (FCC and State Regulators).
10 | Align LATAs and rate centers elimination with “Bill and Keep” implementation date
IP IMG NOTE: This requires action from the FCC.
11 | Implement non-geographic number portability which becomes possible with elimination of LD specific charges to consumers | · Local Number Portability Administration – Working Group (LNPA-WG) by Bridget Alexander (JSI) 9/11/14 | · Local Number Portability Administration – Working Group (LNPA-WG) by Bridget Alexander (JSI) | · Local Number Portability Administration – Working Group (LNPA-WG) by Bridget Alexander (JSI) 11/10/14 | · Local Number Portability Administration – Working Group (LNPA-WG) by Bridget Alexander (JSI) 02/19/15 | · Local Number Portability Administration – Working Group (LNPA-WG) by Bridget Alexander (JSI) 5/18/15
Local Number Portability Administration – Working Group (LNPA-WG)
|  | The LNPA-WG implemented a Non-Geographic Number Porting (NGNP) Sub-Team to identify the issues and impacts of being able to port telephone numbers anywhere in the USA and prepare a white paper for review by the full LNPA WG. The scope of the white paper is to provide an overview of the level of analysis needed to implement NGNP in the industry. In addition, the report will identify NGNP elements that will require FCC attention and/or referral to subject matter experts outside of the LNPA-WG. | No report; group has not met since September. | Report from last meeting has not been approved for distribution. | LNPA - WG did not meet in February. | The May meeting was May 12th & 13th: · A new Tri-Chair was elected: Dawn Lawrence – XO Communications · A sub-team was formed to develop guidelines for new entrants into porting – 1st meeting Thursday, May 21st . Final document will be reviewed by the LNPA WG for approval and posting. · General discussion re: IP and NPAC transition
The Industry Areas of Impact are: Regulatory, Technical and Customer Education.
Sub-team members volunteered to draft text for each:
a. Bridget Alexander – JSI –Customer Education – balexander@jsitel.com
b. Suzanne Addington – Sprint- Technical - Suzanne.M.Addington@sprint.com
c. Deb Tucker – Verizon Wireless - Regulatory - deborah.tucker@verizonwireless.com
d. Teresa Patton – AT&T – will complete the Introduction and Conclusion - TP1393@att.com
Contributions for each area are welcome for incorporation to the draft white paper to be reviewed by the NGNP sub-team on the 9.18 call. The goal is to have a solid draft white paper by November.
|  | · ATIS INC Update provided by Shaunna Forshee (Sprint) | · ATIS INC Update provided by Shaunna Forshee (Sprint) | · ATIS INC Update provided by Shaunna Forshee (Sprint) 11/11/14 | · ATIS INC Update provided by Shaunna Forshee (Sprint) 10/7/14 | · ATIS INC Update provided by Shaunna Forshee (Sprint) 5/20/15 | · ATIS INC Update provided by Connie Hartman on 9/8/15
|  | Issue 748: Assess Impacts on Numbering Resources and Numbering Administration with Transition from Public Switched Telephone Network (PSTN) to Internet Protocol (IP) | INC Whitepaper was sent to Dr. Jordan and Dr. Schulzrinne on 9/19/14 | Nothing new to report. | INC whitepaper was sent to Dr. Jordan and Dr. Schulzrinne on 9/19/14 which addressed the following: Issue 748: Assess Impacts on Numbering Resources and Numbering Administration with Transition from Public Switched Telephone Network (PSTN) to Internet Protocol (IP) | Issue 748: Assess Impacts on Numbering Resources and Numbering Administration with Transition from Public Switched Telephone Network (PSTN) to Internet Protocol (IP) | No new agreements or decisions to report. INC next meeting is September 29 – October 3 in Washington, DC.
|  | · INC has drafted a response to the FCC regarding the impacts of large-scale rate center consolidation during the transition from PSTN to IP. |  |  |  | · INC continues to consider possible next work items in association with the transition to the all-IP network:
|  | · Outlined positive and negative impacts of large-scale rate center consolidation |  |  | · Outlined positive and negative impacts of large-scale rate center consolidation | · Monitoring work of the IEFT STIR WG regarding security and cryptographic certification of TNs
|  | · Documented impacts to carriers networks and systems |  |  | · Documented impacts to carriers networks and systems | · Reviewed the LNPA WG whitepaper on non-geographic number portability
|  | · Identified that regulatory changes would be necessary |  |  | · Identified that regulatory changes would be necessary
|  | · Concluded that large-scale rate center consolidation should be considered when the network architecture of the carriers operating in the area have transitioned from TDM to all-IP |  |  | · Concluded that large-scale rate center consolidation should be considered when the network architecture of the carriers operating in the area have transitioned from TDM to all-IP | · Monitoring the discussion on the IETF MODERN listserv that was created s a result of the numbering testbed workshop.
|  | · FoN WG Update by Suzanne Addington (Sprint) 9/8/14 | · FoN WG Update by Mark Lancaster (AT&T) and Suzanne Addington (Sprint) 10/7/14 | · FoN WG Update Suzanne Addington (Sprint) 11/11/14 |  |  | · FoN WG Update Suzanne Addington (Sprint) 9/10/15
FTN 4: Geographic Issues
|  | The Geographic Numbering sub-committee is discussing the consumer perspective and service implications regarding the geography of telephone numbers and the decoupling or disassociation of numbers from geography. The sub-committee is creating a white paper to be shared with the FoN WG upon completion focusing on the implications for toll-free service. On July 18, 2014, Natalie McNamer (iconectiv) provided a White Paper released by her company entitled: “IP Inter-Carrier Routing: Capabilities to Support IP Services Interconnection” available on their website: http://iconectiv.com/insights/ | A whitepaper is being advanced to the NANC regarding Geographic Routing of Toll-Free Services from FTN #4, with the recommendation to deliver to the FCC as additional information regarding that subject. | FoN Workgroup did not meet in November, no update available. |  |  | A white paper was presented to the NANC in January 2015 regarding Geographic Routing of Toll-Free Services. NANC members requested more time to evaluate the white paper before delivering it to the FCC. A cover letter was approved FoN WG meeting and submitted to NANC at the June 4, 2015 meeting.
|  | · CIGRR (Common Interest Group on Rating and Routing) by Connie Hartmann on 8/11/14: | · CIGRR (Common Interest Group on Rating and Routing) by Connie Hartmann on 9/18/14 | · CIGRR (Common Interest Group on Rating and Routing) by Connie Hartmann on 11/10/14: | · CIGRR (Common Interest Group on Rating and Routing) by Connie Hartmann on 3/11/15: | · CIGRR (Common Interest Group on Rating and Routing) by Connie Hartmann on 5201/15: | · CIGRR (Common Interest Group on Rating and Routing) by Connie Hartmann on 9/8/15
|  | The CIGRR group held a face-to-face meeting the week of July 14, 2014 where CIGRR Issue C204 - Update BIRRDS/LERG to support IP numbering identification and routing was discussed. CIGRR is nearing a resolution on the discussion surrounding the addition of an optional “IP Capable OCN” field on the LRN records in BIRRDS and LERG; which prompted the creation and acceptance of sub-issue C204a - Update LRN data in BIRRDS/LERG to support IP numbering identification and routing to progress this portion of the discussions. The group will continue to discuss other potential changes to BIRRDS and/or LERG in support of issue C204. CIGRR has two conference calls scheduled for issue C204/sub-issue C204a on August 27th and September 23rd as well as a face-to-face meeting the week of October 27th. | Issue C204 - Update BIRRDS/LERG to support IP numbering identification and routing and CIGRR sub-issue C204a - Update LRN data in BIRRDS/LERG to support IP numbering identification and routing. The expected initial closure of sub-issue C204a should occur at the October 2014 CIGRR face-to-face meeting. The group will continue to discuss other potential changes to BIRRDS and/or LERG in support of issue C204. CIGRR has a conference call scheduled for issue C204/sub-issue C204a on September 23rd as well as a face-to-face meeting the week of October 27th. | CIGRR Issue C204 - Update BIRRDS/LERG to support IP numbering identification and routing and CIGRR: A. CIGRR Sub-issue “C204a - Update LRN data in BIRRDS/LERG to support IP numbering identification and routing” was placed into initial closure at the CIGRR meeting held October 28-30, 2014. B. CIGRR Sub-issue “C204b – Update NXD data in BIRRDS/LERG to support IP numbering identification and routing” was accepted and placed into initial closure at the CIGRR meeting held October 28-30, 2014. Sub-issue C204b will result in the addition of an “IP Capable NXX Indictor” field on the NXD records in BIRRDS and carried through to a new LERG file to identify NPA NXX’s for which calls may be routed to over an IP interconnection. C. The next discussion of CIGRR Issue C204 will be via conference call on Tuesday, December 2, 2014. D. The next CIGRR face-to-face meeting is scheduled for January 13-15, 2015 in Orlando, Florida. | .The following CIGRR sub-issues were placed into Final Closure on 12/15/2014 and are expected to be implemented in BIRRDS on May 8, 2015 and in the June 1, 2015 LERG: A. CIGRR Sub-issue C204a - Update LRN data in BIRRDS/LERG to support IP numbering identification and routing. B. CIGRR Sub-issue C204b – Update NXD data in BIRRDS/LERG to support IP numbering identification and routing. C. The current discussion topic at CIGRR in relation to CIGRR Issue 204 - Update BIRRDS/LERG to support IP numbering identification and routing in consideration as to whether or not the addition of URI field in BIRRDS would be appropriate. D. CIGRR Issue C204 will be discussed at the upcoming conference call on April 2, 2015 and at the next face-to-face CIGRR meeting, April 14 - 16, 2015. | The resolutions of CIGRR sub-issues C204a and C204a which were placed into Final Closure on 12/15/2014; have been implemented and will be reflected in the June 1, 2015 LERG™. CIGRR is continuing to discuss the possibility of the addition of a URI field in BIRRDS. CIGRR Issue C204 will be discussed at the next face-to-face CIGRR meeting, July 14-16, 2015. | No new agreements or decisions to report. CIGRR next meeting is October 20-22 in Albuquerque, NM.
|  | · SNAC 8/14 Update: | · SNAC -- No update provided | · SNAC -- No update provided
SNAC Issue 3423: Incorrect Originating Information
FoN is working this Issue and will provide a whitepaper to SNAC for review and possible comment.
12 | Security, anti-spoofing, Privacy (Identity) | ATIS PTSC by Penn Pfautz (AT&T) and Jackie Voss (ATIS) 9/12/14 |  | · ATIS PTSC by Penn Pfautz (AT&) and Jackie Voss (ATIS) -- No update provided
ATIS PTSC: Issue S0111 “Originating party spoofing in IP” is intended to address this topic.
13 | Use of location data
14 | Role of IPv6 and DNS in emerging identifiers
15 | Test Bed Workshop | · 8/24/14 FCC News Release | No updates given | · ATIS TOPS Council's Testbed Initiative Mary Retka (CenturyLink) 11/11/14 |  |  | · ATIS TOPS Council's Testbed Initiative Mary Retka (CenturyLink) 9/8/15
| IP IMG NOTE: This requires action from the FCC. | FCC Chairman Tom Wheeler announced today, August 24, 2014, the appointment of Scott Jordan as Chief Technology Officer. The news release can be found via the following links: https://apps.fcc.gov/edocs_public/attachmatch/DOC-329027A1.docx https://apps.fcc.gov/edocs_public/attachmatch/DOC-329027A1.pdf |  | ATIS TOPS Council's Testbed Initiative sent to FoN Workgroup, INC, ATIS IP NNJ and ATS IPSI |  |  | The ATIS Testbed Team continued to update and finalize the Baseline Document for Phase 1 of the team’s efforts. The Use Cases and Test Plans as well as the Indications of Interest are close to final, with an expectation that they are finalized in the next meeting, or there about. However, contributions are continuing to be provided, and are appreciated. Phase 1 is expected to complete in time for a read out at the October 8th TOPs Council Meeting.
***
· Mary Retka (CenturyLink) and Jay Carpenter (PHONEWORD)
Mary Retka followed up with Dr. Schulzrinne re minutes from the first Test Bed Workshop and scheduling of the next Test Bed Workshop. Jay Carpenter reported that he had asked Dr. Schulzrinne about the test bed status and the response what that the test bed is on hold for now but Dr. Schulzrinne indicated that work will recommence in late summer. (Discussion on www.VUC.me on August 1, 2014; one hour and eighteen minutes into the video, Dr. Schulzrinne gives an update on the FCC Numbering Testbed initiative: http://www.voipusersconference.org/2014/vuc500-dr-henning-schulzrinne/ or http://youtu.be/-pfXBE2POxo)