NOWG/NANPA  5/20/2008  2pm Eastern

NOWG

Paula Hustead		Windstream Communications

Natalie McNamer		T-Mobile

Karen Riepenkroger		Sprint/Nextel

Laura Dalton			Verizon

Bruce Bennett		Qwest

Beth O’Donnell		Cox Communications

Gwen Zahn			Verizon Wireless

Terry Elison			AT&T

Rosemary Emmer		Sprint/Nextel

NANPA

John Manning

Joe Rano

Al Cipparone

Nancy Fears

Tom Foley

Wayne Milby

Joe Cocke

Paula welcomed everyone and turned the meeting over John.

John started with the PIP:

- 5/08 - NAS/PAS interface testing has started.  Target date for implementation is 6/27/08.  FCC permission obtained for 4 hours scheduled maintenance downtime.

- Distributed NNS notice 4/28/08 RCC and Boundary Realignment in LA

- 5/08 – NANPA letter to INC on 500 NXX reclamation posted to the NANPA website (under 5YY Reports).

- 4/21 – Held additional discussions with WI PSC staff on understanding the impacts of two overlapping (715 & 920) relief projects.

- 4/21 – Held discussions with OR PUC staff on the timing of possible public meetings for the 541 NPA project and obtaining public input – referred to the WI and NM commission websites.

- 4/22 – Held discussion with AK RCA staff on relief planning process and provided copy of INC RP guidelines; provided status of 907 NPA.

- 4/23 – As a result of a request, provided to the OK OCC staff the NAS-NNS distribution list of all service providers that received the IPD notice for the OK 918 relief project.

- 4/24 – Held discussions with OCC staff on regulatory process for the 918 NPA project and obtaining public input via website submissions.

- 4/08 – Initiated recovery of 30 UA codes in the VA 757 NPA extending the life of the NPA by more than a year.

- 5/08 – As of 5/16/08, over 160 codes have bee returned to the 500 NXX inventory.

- NANPA responded to 69 NANPA feedback emails from 4/1/08 to 4/30/08.

- (See INC Update for those items from the PIP.)

Complaints:  Received one email via the complaint process.  Individual wanted to port his TN.  NANPA got him in touch with the company he wanted to port to and helped resolve the issue.  The individual sent a Thank You note in appreciation.

John also covered the Code Admin matrix.

Nancy Fears covered the Other Resources matrix.

The NRUF matrix was covered by Al Cipparone.  Job Aides are being updated for June 2008 in preparation for the August 2008 filing.

Wayne Milby and Joe Cocke reported on the NPA Relief Planning activities.

Eastern Region:

# For April 2008

- Six performance measurements were due in April and they were all completed on time.

- We responded to all voicemail and email messages within one business day.

- 4/2 – Facilitated Implementation meeting in response to KY PSC March 31st order.  Industry set start of permissive dialing for March 28, 2010

- 4/4 – NYS PSC initiated proceeding to “Investigate and Evaluate Options for Making Additional Central Office Codes Available in the 315 Area Code Region.”  This was in response to the Public Utility Law Project of New York, Inc. (PULP) petition and reply comments of April 3rd.

- 4/9 – Made Eastern Area NPA Relief Planning presentation at Operations Review session in Sterling, VA.

- 4/11 – Planning Letter 376 published for KY 270 change in the start of permissive dialing.

- 4/15 – Shadowed first WV 304 Industry facilitated implementation meeting.

- 4/16 – Provided various publicly available NY 315 data to NYS DPS Staff as requested for their preparation for public statement hearings and educational forums.

- 4/17 – Initiated recovery of 30 UA codes in the VA 757 NPA extending the life of the NPA by more than a year.

- 4/22 – WV 304 Jeopardy status review call.  Set aside code trigger tripped when set aside codes reached one available on April 8th.

For May 2008

- 5/9 – Submitted INC issue 587 in Initial Closure to revise NPA Relief Planning  Guidelines to address posting a planning letter to the NANPA website 10 business days after regulatory change order is issued.  More time allowed if an implementation meeting is required before PL is posted.

- 5/14 – IN 812 pending petition review call – Industry decided to postpone the filing again and reconvene approximately 30 days after publication of the October 2008 NRUF.  The current exhaust date is 3Q2011.

- 5/22 – KY 270 Jeopardy status review call.  Set aside code trigger tripped when set aside codes reached one available on April 30th.

Also shadowed the WV 304 subcommittee meeting on 5/20/08.

Western Region:

For April 08

- 4/16/08 – Held informal discussions with WI PSC on issues surrounding implementation of adjacent NPA relief projects. Subjects included ANI changes, potential permissive dialing extensions requested by Alarm companies, length of permissive period, LNP functions, dual permissive dialing for two splits, and possible inquiry of industry.

- 4/17/08 - OR 541 NPA - NANPA conducted meeting to review the draft minutes and draft petition on April 17th, both approved- NANPA will file the relief petition no later than May 1, 2008.

- 4/24/08 - OK 918 NPA - NANPA conducted meeting to review the draft minutes and draft petition on April 24th, both approved- NANPA will file the relief petition no later than May 8, 2008.

- 4/24/08 –CA 760 NPA – CPUC-approved the proposed draft decision for a geographic split as the relief method for the 760 NPA on 4/24

- 4/24/08 –CA 818 NPA – CPUC-approved the proposed draft decision for an all services overlay as the relief method for the 818 NPA on 4/24.

- 4/28/08 – CA 760 NPA – NANPA conducted initial implementation meeting for 760-442 Split.

- 4/29/08 – CA 818 NPA – NANPA conducted initial implementation meeting for 818-747 Overlay.

- 4/30/08 – OR 541 NPA – NANPA filed with OPUC relief petition for all services overlay.

For May 08

- 5/7/08 - NANPA published PL-377 and PL-378 for CA 760 split and CA 818 Overlay respectively.

- 5/8/08 – OK 918 NPA – NANPA filed with OCC relief petition for overlay as 1st choice, split as 2nd choice.

Also attended the subcommittee meetings for the NM 505, UT 801, CA 714, CA 818

TRA has performed the utility (in BIRRDS on 5/16/2008) for the 760 NPA split.  Until mandatory, service providers will have to build any new resources on both sides of the split.

Natalie related that she was at a few of the NY public meetings.  Someone from the customer out reach side of the NY DPC stated she was surprised that NANPA wasn’t at the meeting.  Natalie asked if there is a process by which NANPA is in touch with any state commission that is holding any public meeting regarding NPA relief.  Yes, NANPA is in touch with the commissions (usually the telecom staff).  NY is one of the very few commissions that does all of its own NPA relief planning.

FYI:  On 4/25/2008, the NP DPC denied the petition by Public Utility Law Project (PULP).

INC Update (which John handled in Beth’s absence):

Issue 555:  Change to PCS 5YY NXX Part C – Confirmation of Code Activation was moved to Initial Closure at INC 99.  Expected to go to final on 5/30/2008.

Issue 556:  Change to the Part C Confirmation of 900-NXX Code In Service Form was moved to Initial Closure at INC 99.  Expected to go to final on 5/30/2008.

Issue 559:  NPA Code Relief Planning Guidelines to address Customer Complaints was moved to Initial Closure at INC 99.

Issue 587:  NPA Relief Planning Guidelines to address posting a planning letter to the NANPA website after a regulatory change order is issued was accepted and moved to Initial Closure at INC 99.  Expected to go final 5/30/2008.

Issue 588:  Amend Section 2.1.4 of the COCAG Appendix C was accepted and moved to Initial Closure at INC 99.  Expected to go final 5/30/2008.

Issue 589: Sint Maarten Application to Join the NANP was accepted at INC 99.

Issue 591:  Change NANPA’s processing days from 14 calendar to 7 calendar approximately 60 days after the implementation of the mechanized interface between PAS & NAS.

John just received an email from the FCC contract officer that the NANPA contract has been extended until 1/8/2009.

A couple of items of note for June 2008:

6/5 – There will be some state commission calls set up by Brent Struthers.

6/10 – The NANPA portion of the performance report presentation will happen directly after the PA meets with the NOWG.

The next meeting is June 17th @ 2pm Eastern.

Since there were no further questions or comments by the NOWG, the meeting was adjourned.