## Results
NPA RELIEF PLANNING - MONTHLY INTERNAL PERFORMANCE MEASUREMENTS
| Goal | 2001-01-02 |  | 2001-02-01 |  | 2001-03-01 |  | 2001-04-01 |  | 2001-05-01 |  | 2001-06-01 |  | 2001-07-01 |  | 2001-08-01 |  | 2001-09-01 |  | 2001-10-01 |  | 2001-11-01 |  | 2001-12-01
Performance Measurement | % Met | Events | % Met | Events | % Met | Events | % Met | Events | % Met | Events | % Met | Events | % Met | Events | % Met | Events | % Met | Events | % Met | Events | % Met | Events | % Met | Events | % Met
2. 6-week initial meeting notification | 100% | 0 | na | 2 | 100 | 1 | 100 | 1 | 100 | 0 | na | 2 | 100 | 1 | 100 | 2 | 100 | 1 | 100
3. 4-week IPD distribution priot to meeting | 100% | 0 | na | 0 | na | 3 | 100 | 1 | 100 | 0 | na | 0 | na | 3 | 100 | 2 | 100 | 0 | na
4. 2-week distribution of meeting minutes* | 100% | 12 | 100 | 7 | 85.7 | 9 | 100 | 7 | 100 | 8 | 100 | 3 | 100 | 7 | 100 | 10 | 100 | 4 | 100
5. Minutes review 3-weeks after meeting* | 100% | 7 | 100 | 5 | 100 | 5 | 100 | 1 | 100 | 7 | 100 | 3 | 100 | 0 | na | 4 | 100 | 3 | 100
6. 6-week filing of industry relief plan* | 100% | 2 | 100 | 3 | 100 | 0 | na | 0 | na | 2 | 100 | 0 | na | 1 | 100 | 0 | na | 1 | 100
7. NPA assignment request 1 week after regulatory approval | 100% | 2 | 100 | 2 | 100 | 2 | 100 | 4 | 100 | 1 | 100 | 3 | 100 | 1 | 100 | 0 | na | 3 | 100
8. Issue press release within 2 weeks after NPA assignment** | 100% | 0 | na | 1 | 100 | 0 | na | 3 | 100 | 0 | na | 0 | na | 1 | 100 | 0 | na | 2 | 100
9. Hold initial implementation meeting within 45 calendar days after NPA assignment | 100% | 2 | 50 | 2 | 100 | 2 | 100 | 1 | 100 | 3 | 100 | 1 | 100 | 1 | 100 | 5 | 100 | 0 | na
11. Hold jeopardy meeting within 30 calendar days after jeopardy declaration | 100% | 1 | 100 | 0 | na | 1 | 100 | 0 | na | 0 | na | 0 | na | 0 | na | 2 | 100 | 0 | na
12. Post PL on website 3 weeks after the initial implementation meeting | 100% | na | na | na | na | 2 | 100 | 3 | 100 | 4 | 50 | 0 | na | 0 | na | 6 | 100 | 0 | na
13. Post PL on website 10 business days after date of regulatory changes to previously issued PL for NPA relief | 100% | na | na | na | na | 1 | 100 | 1 | 100 | 4 | 100 | 0 | na | 4 | 100 | 1 | 100 | 3 | 100
14. Distribute IPD 4 weeks after date jeopardy was declared, if relief planning has not been initiated | 100% | na | na | na | na | 0 | na | 0 | na | 0 | na | 0 | na | 0 | na | 0 | na | 0 | na
15. Hold industry relief planning meeting 8 weeks after date jeopardy was declared, if relief planning has not been initiated | 100% | na | na | na | na | 0 | na | 0 | na | 0 | na | 0 | na | 0 | na | 0 | na | 0 | na
Totals | 100% | 26 | 96.2 | 22 | 95.5 | 26 | 100 | 22 | 100 | 29 | 96.6 | 12 | 100 | 19 | 100 | 32 | 100 | 17 |  | 0 |  | 0 |  | 0
Average days PMs missed |  | 7 |  | 1 |  | 0 |  | 0 |  | 16 |  | 0 |  | 0 |  | 0 |  | 0
* Or on an alternate date set by the industry at the meeting.
QUALITY SURVEYS OF FACE-TO-FACE INDUSTRY MEETINGS
|  | 2001-01-01 | 2001-02-01 | 2001-03-01 | 2001-04-01 | 2001-05-01 | 2001-06-01 | 2001-07-01 | 2001-08-01 | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01
|  | Avg. | Avg. | Avg. | Avg. | Avg. | Avg. | Avg. | Avg. | Avg. | Avg. | Avg. | Avg.
Face to Face Survey Questions: | Goal | Score | Score | Score | Score | Score | Score | Score | Score | Score | Score | Score | Score
1. Provided adequate notice of the industy meeting |  | 4.5137 | 4.6154 | 4.6429 | 4.6067 | 4.6444 | NA | 4.9333 | 4.6846 | 4.9167
2. Easily able to obtain documents via DDS |  | 4.5601 | 4.5 | 4.7143 | 4.5667 | 4.4534 | NA | 4.6 | 4.4066 | 4.8182
3. Presented the industry with well-developed & reasonable relief alternatives |  | 4.7857 | NA | NA | 4.548 | 4.4048 | NA | 4.7857 | 4.4359 | 4.5
4. Explained relief alternatives effectively |  | 4.7857 | NA | NA | 4.5875 | 4.5317 | NA | 4.8 | 4.6026 | 4.5833
5. Provided satisfactory responses to questions & concerns |  | 4.5673 | 4.5855 | 4.5 | 4.5149 | 4.6833 | NA | 4.9286 | 4.6897 | 4.5833
6. Provided satisfactory information re: CO code assignment history & NPA status |  | 4.5089 | 4.547 | 4.4167 | 4.5756 | 4.5278 | NA | 4.5333 | 4.478 | 4.5
7. Effective facilitator for the meeting |  | 4.7149 | 4.735 | 4.3571 | 4.6332 | 4.7111 | NA | 4.8 | 4.7802 | 4.6667
8. Conducted meeting in impartial manner |  | 4.8232 | 4.7778 | 4.6923 | 4.7056 | 4.8389 | NA | 4.8667 | 4.6846 | 4.9167
9. Adequate opportunity to express opinions |  | 4.8774 | 4.8958 | 4.8571 | 4.8015 | 4.7778 | NA | 4.9333 | 4.9 | 4.8889
10. Overall satisfied with conduct of meeting |  | 4.7899 | 4.7393 | 4.7143 | 4.7271 | 4.7111 | NA | 4.8 | 4.7088 | 4.4167
Number of Meetings |  | 3 | 2 | 1 | 6 | 2 | 0 | 1 | 2 | 1
Number of Survey Responses |  | 41 | 22 | 14 | 90 | 36 | 0 | 15 | 28 | 12
5 = Strongly Agree, 4 = Somewhat Agree, 3 = Neutral, 2 = Somewhat Disagree, 1 = Strongly Disagree
QUALITY SURVEYS OF INDUSTRY CONFERENCE CALLS*
|  | 2001-01-01 | 2001-02-01 | 2001-03-01 | 2001-04-01 | 2001-05-01 | 2001-06-01 | 2001-07-01 | 2001-08-01 | 2001-09-01 | 2001-10-01 | 2001-11-01 | 2001-12-01
|  | Avg. | Avg. | Avg. | Avg. | Avg. | Avg. | Avg. | Avg. | Avg. | Avg. | Avg. | Avg.
Conference Call Survey Questions: | Goal | Score | Score | Score | Score | Score | Score | Score | Score | Score | Score | Score | Score
1. NANPA provided adequate notice of the industry conference call |  | 2001-02-01: 4.8; 2001-05-01: 4.7; 2001-08-01: 4.9136
2. The information provided prior to the call was sufficient to allow me to participate knowledgeably on the call. |  | 2001-02-01: 4.3; 2001-05-01: 4.7; 2001-08-01: 4.7549
3. I had no difficulty dialing in & connecting to the conference call. |  | 2001-02-01: 4.8; 2001-05-01: 5; 2001-08-01: 4.8179
4. The conference call facilities (sound quality, low noise) were satisfactory |  | 2001-02-01: 4.6; 2001-05-01: 4.7; 2001-08-01: 4.8364
5. NANPA was an effective facilitator for the conference call. |  | 2001-02-01: 4.7; 2001-05-01: 4.8; 2001-08-01: 4.8722
6. NANPA conducted the conference call in an impartial manner. |  | 2001-02-01: 4.6; 2001-05-01: 4.9; 2001-08-01: 4.916
7. NANPA was well prepared for the meeting. |  | 2001-02-01: 4.8; 2001-05-01: 4.8; 2001-08-01: 4.8722
8. I had an adequate opportunity to express my opinions during the call |  | 2001-02-01: 4.8; 2001-05-01: 4.9; 2001-08-01: 4.95
9. Overall, I am satisfied with NANPA's conduct of the conference call |  | 2001-02-01: 4.7; 2001-05-01: 4.9; 2001-08-01: 4.9167
Number of Conference Calls |  | 2001-02-01: 10; 2001-05-01: 10; 2001-08-01: 9
Total number of survey responses |  | 2001-02-01: 27; 2001-05-01: 58; 2001-08-01: 68
5 = Strongly Agree, 4 = Somewhat Agree, 3 = Neutral, 2 = Somewhat Disagree, 1 = Strongly Disagree
* Conference call surveys are conducted on all conference calls during one month each quarter.