NOWG Meeting Notes – December 15, 2003

Participants:

Bruce Bennett

Cathie Capita

Jim Castagna 

Joanne Edelman

Rosemary Emmer

Paula Hustead

Beth O’Donnell

Reviewed and noted dates for the pooling administration timeline.

January 13, 2004 – NANC and FCC endorses PA survey

January 20, 2004 – Pooling Administrator survey distributed

February 20, 2004 – Pooling Administrator survey due back to NOWG co-chairs

March 2004 – Analyze survey results

April 13-15, 2004 – Operational Review of pooling administrator in Concord, CA

May 10 – 14, 2004 – NOWG meets in Denver to complete PA operational review results

ACTION ITEM:  Jim to complete cover letter to Mark Oakey and send to NOWG for review by end of week.

Survey for PA is final unless someone sees a substantial problem.  

ACTION ITEM:  Jim to send final survey and comments back to Shannon Collins by end of week.

Next call with NANPA is this Thursday, December 18, 2004.  

NANPA surveys are continuing to come to Jim and Karen.  

ACTION ITEM:  Because some of the states have already filled out their survey, using the last draft, Jim will review to make sure there isn’t any issues brought up that should be incorporated into the final survey.

ACTION ITEM:  Jim and Karen M. will sync up status of surveys to share with NOWG on next call.

Discussion regarding the NANC presentation on January 13, 2003.  The presentation will focus on the NANPA and PA surveys.  The NANPA results from meetings of NOWG/NANPA.

ACTION ITEM:  Jim/Karen M. will send NANC presentation to NOWG for review no later then 1/7/03.

Discussion of PA complaints.  Agreement that any complaints regarding the PA should go to the PA first.  Issues not resolved should then be taken to the contracting officer or the FCC.  

There should be some type of paper trail of formal complaints.  There should be something on the PA website to assist the Industry on what the formal complaint process regarding pooling should be.

ACTION ITEM:  Joanne and Paula to put a draft together for the NOWG to review on a formal complaint process for the PA.

The meeting notes for 9/12/03 and 12/10/03 have been sent to John Manning for posting.

Discussion on Change Order #25

Further discussions on how the cost for Change order 25 should be less then change order 21 since the majority of the components have already been established to pull a report.  Still don’t understand from the response from Shannon Collins why the cost would continue to be the same.  

Rather then accept the change order and put comments to the FCC on pricing, it was decided Jim should write a note to Shannon Collins, stating there could be another alternative to creating the Part 4 report using data from the Part 1A report.

ACTION ITEM:  Jim to put together letter to Shannon Collins asking about a possible alternative for CO #25.

Scheduled calls:

December 18, 2003   Monthly NOWG/NANPA call

January 9, 2004  NOWG call

